## Issue register
Issue register
Fictional example — completion is not evidence of verified closure. Blue cells are intended inputs; fixed observations and formula checks are protected.
Field | Fictional record
Issue ID | LF-ISS-017
Process / period | Vendor master changes ¦ Q2
Finding | Secondary approval was not evidenced for 3 of 25 changes tested.
Condition observed | Approval timestamp was absent from the retained change record.
Evidence supplied | Email stating ‘team retrained’; no population, configuration evidence, or retest output.
Evidence sufficiency | Insufficient
Management response | Retrain the analyst who missed the approval.
Root cause status | Not yet evidenced
Closure status | Open
Owner | Morgan Lee
Decision note: a completed action can address a symptom and still leave root cause, evidence, and closure review unresolved.
Evidence check (formula)
This formula identifies record readiness only. It does not determine severity, effectiveness, or a closure decision.
Evidence reference / reviewer working notes (record the post-change population, method, exceptions, and retained source reference):
Additional follow-up or decision context:

## Action plan
Action plan
Fictional action plan — planned result and evidence request help test whether an action addresses the observed condition, not merely whether it was completed.
Action ID | Proposed change | Evidence requested | Implementation / retest
ACT-017A | Retrain analyst on approval step. (Symptom-only action retained for history.) | Attendance record only — insufficient for closure. | Complete / Follow-up needed
ACT-017B | Require system-captured approver ID and timestamp before vendor record can be released. | Configuration change record; post-change population; sample retest with retained approvals. | In progress / Not started
Action status
Formula counts a recorded implementation status. It cannot determine whether evidence supports retest or closure.
Implementation evidence reference / release record:
Retest scope, population, exceptions, and reviewer reference:

## Closure review
Closure review
Fictional closure review — complete the review deliberately. The formula cannot provide a severity, effectiveness, or assurance conclusion.
Review question | Recorded response | Reviewer note / reference
Is the original condition and population clearly identified? | Yes | Issue register LF-ISS-017; 3 of 25 sample observation.
Does the management response describe a root-cause change rather than only retraining? | No | ACT-017A retained for history; ACT-017B added.
Is implementation evidence present? | Pending | Add approved configuration record and release evidence.
Is a post-change retest result recorded? | Pending | Specify period, population, method, exceptions, and reviewer.
Independent reviewer decision | Follow-up required | Select only after the documented review; this remains a manual independent judgment.
Calculated status |  | Readiness agrees with the issue and action records; it does not replace the documented independent judgment.
Independent reviewer basis / evidence references:
Follow-up owner, next review date, or documented closure rationale:

## How to use
How to use
A consulting-quality starter, not a product export or Workiva interface. Fixed fictional observations give a concrete starting point; blue rows are optional meeting notes.
1. Record the condition and what evidence actually supports it.
2. Keep a symptom-only response visible, then define a separate root-cause action if warranted.
3. Record implementation evidence and retest scope before selecting a closure decision.
4. Use ‘Follow-up required’ when support remains incomplete. Verified closure is a documented independent-review decision, not an automatic status.
Meeting notes / evidence to request next:
Owner and next review date: