## Read me
LOCKFIELD / GRC MIGRATION PLANNER
How to use this planning workbook
Fictional worked tabs demonstrate the level of detail. Blank tabs are for planning; this workbook does not connect to, upload to, or configure Workiva.
Planning surface | How to use it
Start with an inventory | List record sets, history, formats, owners, access constraints, and candidate disposition. Do not assume all historical material should move.
Map semantics and relationships | Define business meaning, transformations, stable identifiers, and relationship behavior. Implementers configure the agreed target; buyers decide scope, ownership, and retention.
Make preservation decisions explicit | “Retain elsewhere” needs a retrieval route. “Hold” means an unresolved decision and should not be treated as ready.
Reconcile after an agreed load or extraction | Provide expected and received values. Formula results distinguish unresolved input, agreement, and exception; a formula does not approve a release.
Run practical UAT | Use realistic roles and historical paths: controls, risks, tests, issues, closure support, attachments, and access. Record what was observed.
Use the fictional example carefully | Northwind Holdings, people, IDs, counts, and records are invented for teaching. Replace all example content before applying this workbook to a client program.
Boundary | This resource provides migration planning guidance. Workiva functionality, available objects, imports, roles, and licenses depend on the selected solution and configuration. Validate implementation choices with the appropriate product and business owners.

## Worked inventory
LOCKFIELD / GRC MIGRATION PLANNER
Worked source inventory — fictional example
Northwind Holdings is fictional. It shows decision-level detail, not a required Workiva import layout.
Source object / record set | Business owner | Volume / period | Current location & format | Historical span | Quality or access observation | Initial disposition
Control library | Jordan Lee · SOX lead | 84 active / 31 retired | Controlled spreadsheet + evidence folder | FY2022–FY2026 | Retired controls share IDs with a legacy archive | Preserve active; retain retired elsewhere
Risk register | Mina Patel · Risk | 57 current | GRC export CSV | FY2024–FY2026 | Three risks have no linked control reference | Clean before mapping
Test plans & results | Avery Brooks · Internal Audit | 146 tests / 22 exceptions | Audit tracker workbook | FY2023–FY2026 | Test IDs remain stable; evidence paths do not | Preserve with relationship review
Issues & action plans | Riley Chen · Compliance | 19 open / 46 closed | Issue log CSV + attachments | FY2021–FY2026 | Closed issues need audit retrieval, not operational use | Retain elsewhere; migrate open
Evidence attachments | Named control owners | 612 files | Folder hierarchy / PDF, XLSX, MSG | FY2023–FY2026 | 12 paths contain restricted payroll support | Decision pending: access & retention
User / owner reference list | GRC administrator | 38 people | Directory export | Current | Four departed owners need reassignment | Clean before mapping

## Worked mapping
LOCKFIELD / GRC MIGRATION PLANNER
Worked field & relationship mapping — fictional example
Map source semantics to a buyer-approved target configuration. “Target configuration” is an implementer decision, not a universal Workiva schema.
Source object | Source field / relationship | Example source value | Target business meaning | Mapping / transform rule | Relationship or history decision | Decision state
Control | Control ID | AP-014 | Stable reference for control | Keep literal ID; check duplicate across retired library | Link to assigned risk and current owner; retired record stays retrievable | Confirmed
Control | Owner email | j.lee@northwind.example | Accountable person | Resolve against current directory; flag departed users | Do not create an owner relationship until reassignment is approved | Needs decision
Risk | Related control IDs | AP-014; AP-018 | Risk-to-control association | Split semicolon list; report unmapped IDs | Maintain many-to-many association where selected configuration supports it | Test in UAT
Test result | Result | Exception — invoice approval missing | Testing conclusion | Normalize outcome vocabulary with policy owner | Retain link to test plan and issue, not just narrative text | Confirmed
Issue | Closure evidence path | /FY25/Q4/Issue-19.pdf | Closure support location | Keep source path as reference; decide file migration separately | Closed issue remains in archive with retrieval route | Needs decision
Attachment | Classification | Restricted payroll | Access / retention classification | Do not migrate until access owner approves destination | Preserve source custody and document exception | Hold

## Worked decisions
LOCKFIELD / GRC MIGRATION PLANNER
Worked preservation decisions — fictional example
A preservation decision names the business rationale and retrieval route. It does not authorize records disposal or change retention obligations.
Record set | Decision | Business rationale | Required approval / owner | Retrieval or preservation route | Status / next action
Active controls and current relationships | Migrate | Operational reporting and assessment | SOX lead | Target configuration after mapping sign-off | Ready for configuration
Retired controls FY2022–FY2023 | Retain elsewhere | Historical audit retrieval; no current operation | Records owner | Read-only archive + index of retained IDs | Archive route to validate
Closed issues | Retain elsewhere | Closure history may be requested | Compliance lead | Original issue log and file index | Confirm retention owner
Open issues and actions | Migrate | Current remediation monitoring | Compliance lead | Target configuration with link back to source ID | Ready for mapping
Restricted payroll attachments | Hold | Access and retention decision unresolved | Privacy / HR owner | Existing restricted folder; no transfer | Unresolved input — do not migrate
Orphaned owner references | Clean | Departed user references cannot be assigned automatically | GRC administrator | Exception list with approved replacement owner | Needs approved reassignment

## Worked reconciliation
LOCKFIELD / GRC MIGRATION PLANNER
Worked reconciliation — fictional example
PASS means a named scope has matching non-negative whole-number counts. It does not prove population completeness or relationship completeness; review mapping and UAT evidence.
Check / population (required) | Expected count (required; whole number ≥ 0) | Received count (required; whole number ≥ 0) | Formula result | Reviewer note / exception owner
Active controls count | 84 | 84 |  | Population count agrees; sample relationships separately.
Active risk count | 57 | 57 |  | Population count agrees.
Open issue count | 19 | 18 |  | One issue intentionally held pending restricted attachment decision.
Control IDs without current owner | 0 | 4 |  | Four departed owners awaiting reassignment.
Tests with linked issue where exception exists | 22 | 22 |  | Review selected links during UAT.
Attachment index entries approved for transfer | 600 | 600 |  | Twelve restricted files are excluded and retained in source custody.

## Worked UAT
LOCKFIELD / GRC MIGRATION PLANNER
Worked UAT scenarios — fictional example
UAT validates agreed business behavior in the selected configuration. It is not a claim about a standard product endpoint, license, or automated migration behavior.
Scenario | Test data / role | Practical UAT steps | Expected evidence to review | Result | Observed note / defect reference
Control relationship | Control AP-014; risk R-007 | Open control; locate linked risk; confirm owner is the approved current person. | Relationship is visible, source ID is traceable, and role can access only intended record. | Pass | Owner relationship reviewed with GRC admin.
Historical test & exception | Test T-2025-034 with exception | Open test result; trace exception to linked open issue. | Test conclusion, issue reference, and source identifier remain intelligible to reviewer. | Pass | Fictional chain completed.
Closed issue retrieval | Closed Issue-19 | Use agreed archive route; locate closure record and linked evidence reference. | Archive returns record with retention context; no claim that it is operationally migrated. | Not run | Archive owner to demonstrate retrieval.
Restricted attachment | Payroll attachment index 441 | Attempt access with non-authorized reviewer; confirm documented hold decision. | No unintended access; exception log names approver and source custody route. | Blocked | Awaiting privacy / HR decision.
Reconciliation exception | Open issues 19 expected / 18 received | Review count mismatch; identify held record and decision. | Exception is explained, owned, and not relabeled as a pass. | Pass with exception | Issue-19 held; see preservation decision.
Role-based review | Reviewer account | Review assigned records and attachments; confirm access outcome with account owner. | Observed access matches approved scope; deviations are logged. | Not run | Run after roles are configured.

## Blank inventory
LOCKFIELD / GRC MIGRATION PLANNER
Blank source inventory
Blue cells are for your team. Leave an unknown field blank; that is an unresolved input, not a pass.
Source object / record set | Business owner | Volume / period | Current location & format | Historical span | Quality or access observation | Initial disposition

## Blank mapping
LOCKFIELD / GRC MIGRATION PLANNER
Blank field & relationship mapping
Capture semantic intent first; an empty target field means configuration is unresolved, not ready.
Source object | Source field / relationship | Example source value | Target business meaning | Mapping / transform rule | Relationship or history decision | Decision state

## Blank decisions
LOCKFIELD / GRC MIGRATION PLANNER
Blank preservation decisions
Use this surface to distinguish migration scope from archive, cleanup, legal hold, access, or policy decisions.
Record set | Decision | Business rationale | Required approval / owner | Retrieval or preservation route | Status / next action

## Blank reconciliation
LOCKFIELD / GRC MIGRATION PLANNER
Blank reconciliation
Blue cells marked required define the population and valid counts. PASS is a review indicator only: also review population completeness, relationships, and UAT evidence.
Check / population (required) | Expected count (required; whole number ≥ 0) | Received count (required; whole number ≥ 0) | Formula result | Reviewer note / exception owner

## Blank UAT
LOCKFIELD / GRC MIGRATION PLANNER
Blank UAT scenarios
Write observable steps and expected evidence. Use “not run” until the scenario is actually exercised.
Scenario | Test data / role | Practical UAT steps | Expected evidence to review | Result | Observed note / defect reference
Not run
Not run
Not run
Not run
Not run
Not run